## Instructions
ITC327W Project Progress and Contribution Workbook
Use this workbook throughout the semester. Update it after each project phase and submit the same workbook again so that progress can be tracked over time.
Sheet | Purpose | Evidence and Accountability Rules
Project Overview | Enter the group and project details. The dashboard summarises task progress automatically. | 1 | Every student must be assigned meaningful work in Microsoft Project.
Task Progress | Record planned and completed tasks, responsible students, dates, status, percentage completed and evidence. | 2 | Completed work must be supported by evidence such as GitHub activity, meeting records, document sections, screenshots or stakeholder communication.
Individual Contributions | Record the work personally completed by each student. Every entry must have evidence. | 3 | GitHub commits are not the only evidence. Planning, interviewing, documentation, coordination and quality review also count.
Stakeholder Engagement | Record meetings, calls and emails with the stakeholder and the main outcomes. | 4 | Do not record work as completed by a student when it was completed by someone else.
Challenges & Actions | Record project challenges, their effect and the corrective action taken. | 5 | Do not place passwords, API keys, identity numbers, private contact details or confidential records in this workbook or on GitHub.
Phase Summary | Provide a short summary of the phase, including achievements, outstanding work and participation concerns. | 6 | The confidential individual peer evaluation must be completed separately on Blackboard.
Group Reflection | Complete one shared reflection after each phase. Be honest and specific.
Recommended Update Points
|  | Unit 1 / Phase 1 | Planning, stakeholder engagement, requirements and initial SRS
|  | Phase 2 | Architecture, UML, ERD and interface design
|  | Phase 3 | Development, integration, testing and demonstration
|  | Final | Overall project summary and final reflection

## Project Overview
Project Overview and Progress Dashboard
Project Information | Group Response | Task Status | Count
Group name or number | Group W | Completed | 11
Project title | LifeStyle Square CarWash Management System | In Progress | 0
Stakeholder or organisation | LifeStyle Square | Not Started | 0
Group mentor | Mrs Mbele | Delayed | 0
Reporting phase | Unit 1 / Phase 1 | Blocked | 0
Reporting period | 25 August 2026 - 03 September 2026 | Overdue | 0
Overall status | Completed
Overall % complete | 100% | Contribution Summary | Count
Main achievement | Identified stakeholder and documented initial requirements | Contribution entries | 6
Main challenge | Securing stakeholder availability for meetings | Verified entries | 6
Next planned activity | Finalise SRS document and submit | Unverified entries | 0
|  | Stakeholder engagements | 4

## Task Progress
Task Progress Tracker
Task ID | Reporting Phase | Activity | Task Description | Assigned Student | Start Date | Due Date | Status | % Complete | Evidence / Link | Verified by Group | Lecturer Comment | Progress Flag
U1-01 | Unit 1 / Phase 1 | Activity 1.1 | Identify and confirm the external stakeholder | All members | 2026-08-25 | 2026-08-28 | Completed | 100 | Meeting minutes | Yes |  | Completed
U1-02 | Unit 1 / Phase 1 | Activity 1.1 | Document the current process and problem | Charity Nkasi | 2026-08-28 | 2026-08-30 | Completed | 100 | Document | Yes |  | Completed
U1-03 | Unit 1 / Phase 1 | Activity 1.1 | Define the project aim, objectives and scope | All members | 2026-08-28 | 2026-09-02 | Completed | 100 | Document | Yes |  | Completed
U1-04 | Unit 1 / Phase 1 | Activity 1.2 | Prepare stakeholder interview questions | Lebona Lehlohonolo | 2026-08-28 | 2026-09-03 | Completed | 100 | Interview questions | Yes |  | Completed
U1-05 | Unit 1 / Phase 1 | Activity 1.2 | Conduct and document the stakeholder interview | Tebogo Ramaano | 2026-08-30 | 2026-09-03 | Completed | 100 | Interview notes | Yes |  | Completed
U1-06 | Unit 1 / Phase 1 | Activity 1.3 | Compile the initial SRS | Mamafha Mbulaheni | 2026-09-02 | 2026-09-03 | Completed | 100 | SRS document | Yes |  | Completed
U1-07 | Unit 1 / Phase 1 | Activity 1.3 | Create the initial Microsoft Project schedule | Lahluma Maselana | 2026-09-02 | 2026-09-03 | Completed | 100 | MS Project file | Yes |  | Completed
U1-08 | Unit 1 / Phase 1 | Activity 1.3 | Create and configure the GitHub repository | Lebona Lehlohonolo | 2026-09-02 | 2026-09-03 | Completed | 100 | GitHub link | Yes |  | Completed
U1-09 | Unit 1 / Phase 1 | Activity 1.3 | Create the initial Supabase project | Myeni Nelisiwe | 2026-09-02 | 2026-09-03 | Completed | 100 | Supabase link | Yes |  | Completed
U1-10 | Unit 1 / Phase 1 | Activity 1.3 | Complete the progress report and contribution record | All members | 2026-09-03 | 2026-09-03 | Completed | 100 | Progress Report | Yes |  | Completed
U1-11 | Unit 1 / Phase 1 | Activity 1.3 | Complete the Unit 1 group reflection | All members | 2026-09-02 | 2026-09-03 | Completed | 100 | Group reflection | Yes |  | Completed
Formulas:
Progress Flag = IF([Task Description]="","",IF([Status]="Completed","Completed",IF([Status]="Blocked","Blocked",IF([Status]="Delayed","Delayed",IF(AND([Due Date]<>"",[Due Date]<TODAY(),[Status]<>"Completed"),"Overdue","On Track")))))

## Individual Contributions
Individual Contribution Record
Student Name | Student Number | Reporting Phase | Activity | Assigned Responsibility | Work Personally Completed | Date Completed | Hours Spent | Evidence / Link | Verified by Group | Verification Date | Notes
Lebona Lehlohonolo | 222005563 | Unit 1 / Phase 1 | Activity 1.1, 1.2, 1.3 | Stakeholder communication, prepared interview questions, created GitHub repository | contacted stakeholder, prepared interview questions, set up GitHub repo | 2026-09-03 | 8 | pictures,records, meeting notes, GitHub link | Yes | 2026-09-03 | Completed all tasks on time
Nelisiwe Myeni | 224093153 | Unit 1 / Phase 1 | Activity 1.1, 1.2, 1.3 | Created Supabase project, participated in meetings | Set up Supabase project, attended all meetings | 2026-09-03 | 6 | Supabase link, meeting minutes | Yes | 2026-09-03 | Participated in all meetings
Charity Nkasi | 222043740 | Unit 1 / Phase 1 | Activity 1.1, 1.2, 1.3 | Documented current process, compiled initial SRS | Documented current process, compiled SRS document | 2026-09-03 | 10 | SRS document, meeting minutes | Yes | 2026-09-03 | Compiled SRS successfully
Tebogo Ramaano | 224003699 | Unit 1 / Phase 1 | Activity 1.1, 1.2, 1.3 | Conducted and documented stakeholder interview | Conducted stakeholder interview, documented findings | 2026-09-03 | 7 | Interview notes, meeting minutes | Yes | 2026-09-03 | Conducted interview well
Lahluma Maselana | 224131946 | Unit 1 / Phase 1 | Activity 1.1, 1.2, 1.3 | Created Microsoft Project schedule | Created MS Project schedule with tasks and timeline | 2026-09-03 | 5 | MS Project file | Yes | 2026-09-03 | Created schedule on time
Mamafha Mbulaheni | 224074556 | Unit 1 / Phase 1 | Activity 1.1, 1.2, 1.3 | Compiled initial SRS, participated in meetings | Contributed to SRS compilation, attended meetings | 2026-09-03 | 6 | SRS document, meeting minutes | Yes | 2026-09-03 | Contributed to SRS and meetings

## Stakeholder Engagement
Stakeholder Engagement Record
Date | Reporting Phase | Type of Engagement | Purpose | Students Present | Stakeholder Present / Role | Main Findings | Action Required | Evidence / Link
2026-08-25 | Unit 1 / Phase 1 | Meeting | Identify and confirm stakeholder, discuss project scope | Lebona Lehlohonolo, Nelisiwe Myeni, Charity Nkasi, Tebogo Ramaano, Lahluma Maselana, Mamafha Mbulaheni | Mr Maxwell Mkhwane/Owner | Stakeholder confirmed participation, project scope discussed and agreed | Schedule next meeting for interview | Meeting voice recording and pictures and minutes
2026-08-28 | Unit 1 / Phase 1 | Meeting | Schedule the next physical meeting for stakeholder interview | Lebona Lehlohonolo | Mr Maxwell Mkhwane/Owner | Agreed on 30 August for interview | Confirm meeting time and venue | WhatsApp screenshot/https://call.whatsapp.com/voice/wuTRe62cVztxOzj0zK91mW
2026-08-30 | Unit 1 / Phase 1 | Site Visit | Conduct stakeholder interview to gather requirements | Lebona Lehlohonolo, Nelisiwe Myeni, Charity Nkasi, Tebogo Ramaano, Lahluma Maselana, Mamafha Mbulaheni | Mr Maxwell Mkhwane/Owner | Identified current process, challenges, and system requirements | Document requirements in SRS | Interview notes, Recording, Photos
2026-09-02 | Unit 1 / Phase 1 | Online Meeting | Follow-up on requirements clarification and outstanding questions | Lebona Lehlohonolo, Nelisiwe Myeni, Charity Nkasi, Tebogo Ramaano, Lahluma Maselana, Mamafha Mbulaheni | Mr Maxwell Mkhwane/Owner | Requirements clarified, outstanding questions answered | Finalise SRS document | Meeting recording, Teams chat log/https://teams.microsoft.com/meet/334157851730437?p=Y2LxEuE8LRjLfesmIC

## Challenges & Actions
Challenges and Corrective Actions
Date Identified | Reporting Phase | Challenge | Effect on Progress | Corrective Action | Responsible Student | Target Date | Status
2026-08-28 | Unit 1 / Phase 1 | Stakeholder availability for initial meeting | Delayed confirmation of stakeholder participation | Rescheduled meeting to accommodate stakeholder's availability | Lebona Lehlohonolo and charity Nkasi | 2026-08-30 | Resolved
2026-08-30 | Unit 1 / Phase 1 | Some members could not attend the physical meeting | Limited participation during stakeholder interview | Shared meeting recording and notes with absent members | Nelisiwe Myeni and Mamafha Mbulaheni | 2026-08-31 | Resolved
2026-09-02 | Unit 1 / Phase 1 | Unclear requirements from initial interview | Delayed drafting of SRS | Scheduled follow-up Teams meeting to clarify requirements | Ramaano Teboho And Lahluma Maselana | 2026-09-02 | Resolved

## Phase Summary
Phase Progress Summary
Summary Information | Group Response | Phase Completion Checklist
Reporting phase | Unit 1 / Phase 1 | Initial or updated SRS completed | Yes
Reporting period | 25 August 2026 - 03 September 2026 | Progress report updated | Yes
Overall phase status | Completed | Individual contributions recorded | Yes
What was completed during this phase? | Stakeholder identified and confirmed, initial meeting conducted, requirements gathered through interview, SRS drafted, project schedule created, GitHub repository set up, Supabase project created | Stakeholder engagement recorded | Yes
What remains incomplete? | None for Phase 1 | Challenges and actions updated | Yes
Why is it incomplete? | N/A | Group reflection completed | Yes
Which contributions were particularly important? | Stakeholder communication by Lebona and Lahluma , SRS compilation by Charity and Neli, scheduling by Tebogo and Mbulaheni, and overall coordination by all members | Microsoft Project updated | Yes
Were there participation concerns? | No, all members contributed and participated effectively | GitHub evidence available | Yes
What will the group improve in the next phase? | Better time management, more frequent communication, and earlier task completion | Confidential peer check completed | Yes
Main priority for the next phase | Architecture design, UML diagrams, ERD, and interface design

## Group Reflection
Group Reflection
Reflection Information | Group Response | Reflection Guidance
Reporting phase | Unit 1 / Phase 1 | Length | Approximately 300–400 words in total.
Project title | LifeStyle Square CarWash Management System | Focus | Discuss the group’s actual experience, not the activity instructions.
Most important learning from this phase | Effective teamwork requires clear communication and flexibility. Each member has different strengths and contributions matter in different ways. | Honesty | Identifying a genuine challenge will not disadvantage the group when an improvement action is provided.
What went well and why? | The group communicated well through meetings and WhatsApp. Tasks were completed on time and everyone was willing to help each other when needed. | Evidence | Ensure that claims about participation agree with the contribution record, Microsoft Project and GitHub.
What was difficult and why? | Coordinating schedules was challenging as some members had different availability. However, we accommodated each other by sharing meeting notes and recordings. | Research use | Student work may only be used for research after the required ethical approval and consent processes.
How were tasks divided among members? | Tasks were divided based on each member's strengths. Lebona handled stakeholder communication, Charity compiled the SRS, Tebogo managed scheduling, Nelisiwe set up Supabase, Lahluma created the MS Project schedule, and Mamafha contributed to documentation and meetings.
Did all members contribute fairly? Explain. | Yes, all members contributed to the project. Each member completed their assigned tasks and participated in meetings. Those who could not attend physically still contributed remotely.
How did the group handle disagreements or delays? | The group handled disagreements by discussing issues openly and finding common ground. We respected each other's opinions and made decisions as a team.
What did the group learn from the stakeholder? | The group learned about the current car wash processes, the challenges the business faces, and the specific features the stakeholder expects from the system. The stakeholder highlighted the importance of efficiency, customer record management, and accurate payment tracking. Through the engagement, we gained a clear understanding of the functional requirements, including wash package selection, customer history, employee management, and daily reporting. The stakeholder also shared frustrations with the manual process, which helped us identify key problems the system needs to solve.
Improvement action 1 for the next phase | Improve time management by setting earlier deadlines for tasks to avoid last-minute pressure.
Improvement action 2 for the next phase | Schedule more frequent check-in meetings to track progress and address issues earlier.
Priority for the next phase | Architecture design, UML diagrams, ERD, and interface design.